## Sheet1
Milestone | Deliverable | Time | Payment | Remarks
1 | Basic Simulation for Preamble Detection | 15 days | 80712 | 10% of Overall Cost
2 | Basic Simulation for Equalizer, Time and Frequency Synchronization | 45 days | 322848 | 40% of Overall cost
3 | Hardware compatible MATLAB implementation | 90 days | 403560 | Final Payment
| Total |  | 807120

## Sheet2
S.No | Head | Cost
1 | Man power | 200000
2 | Hardware/Software | 200000
3 | Contingency | 20000
4 | Travel | 50000
5 | Consumables | 50000
| Total | 520000
4 | Institute overhead cost (20% of project cost) | 104000
5 | Gross Total | 624000
6 | State GST (9% of overall cost) | 56160
7 | Central GST (9% of overall cost) | 56160
| Grand Total | 736320
184080